## app
|  | Department of Education-Division of Tuguegarao City NON CSE Annual Procurement Plan - FY 2020 | [10 empty] | Department of Budget and Management Procurement Monitoring Report as of month/day/2006
Code (PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (brief description of Program/Activity/Project) | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [8 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  | Pre-Proc Conf | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Delivery/ Accept
| Conduct of Curriculum Implementation | CID | Shopping | June 23,2020 | N/A | June 29,2020 | June 30,2020 | GoP | 17500 | 17500 | 0
| Conduct of Science and Technology Week | CID | Shopping | June 23,2020 | N/A | June 29,2020 | June 30,2020 | GoP | 20500 | 20500 | 0
| Conduct of Science Fair | CID | Shopping | Sept. 21, 2020 | N/A | Sept.25,2020 | Sept.25,2020 | GoP | 30450 | 30450 | 0
| 2020 Festival of Talents(Division,Regional,National) | CID | NP-53.9 - Small Value Procurement | Jan.27,2020 | N/A | Jan.31,2020 | Jan.31,2020 | GoP | 266678 | 266678 | 0
| 3rd Division Mathematics Camp | CID | Shopping | Nov.23,2020 | N/A | Nov.27,2020 | Nov.27,2020 | GoP | 28750 | 28750 | 0
| Project Pangiadde Ta Pakannammu Ta Totolay Ta Barangay | CID | Shopping | Nov.23,2020 | N/A | Nov.27,2020 | Nov.27,2020 | GoP | 12050 | 12050 | 0
| Search for Best ALS Instructional Material | CID | Shopping | Oct.26,2020 | N/A | Oct.30,2020 | Oct.30,2020 | GoP | 5400 | 5400 | 0
| Search for Effective & Efficient CLC | CID | Shopping | Nov.23,2020 | N/A | Nov.27,2020 | Nov.27,2020 | GoP | 7800 | 7800 | 0
| Conduct of Literary Joust | CID | Shopping | Aug.21,2020 | N/A | Aug.26,2020 | Aug.26,2020 | GoP | 18000 | 18000 | 0
| Conduct of Reading Festival | CID | Shopping | Oct.26,2020 | N/A | Oct.30,2020 | Oct.30,2020 | GoP | 20000 | 20000 | 0
| Conduct of Division Asean Quiz | CID | Shopping | June 19,2020 | N/A | June24,2020 | June24,2020 | GoP | 3550 | 3550 | 0
| Conduct of Division Level Tourism Quiz | CID | Shopping | July 13, 2020 | N/A | July 17, 2020 | July 17,2020 | GoP | 5346 | 5346 | 0
| PopQuiz and On-the-Spot Skills Exhibition Competition | CID | Shopping | July 13, 2020 | N/A | July 17, 2020 | July 17,2020 | GoP | 10500 | 10500 | 0
| Search for the Best Kindergarten Classroom | CID | Shopping | Dec.1,2020 | N/A | Dec.4,2020 | Dec.4,2020 | GoP | 5000 | 5000 | 0
| Orientation cum workshop for storybook illustrators and graphic designers | CID | NP-53.9 - Small Value Procurement | April 1,2020 | N/A | April 7,2020 | April 7,2020 | GoP | 65000 | 65000 | 0
| Capacity Building for Filipino Teachers on Critical Content | CID | NP-53.9 - Small Value Procurement | April 1,2020 | N/A | April 7,2020 | April 7,2020 | GoP | 94000 | 94000 | 0
| Capacity Building for School Paper Advisers on Production and Management of School Publication | CID | NP-53.9 - Small Value Procurement | April 1,2020 | N/A | April 7,2020 | April 7,2020 | GoP | 100000 | 100000 | 0
| Writeshop on DLP in Priority Learning Areas in Grade 6 | CID | NP-53.9 - Small Value Procurement | April 1,2020 | N/A | April 7,2020 | April 7,2020 | GoP | 179980 | 179980 | 0
| Training Workshop on the Conduct of Science Investigatory Projects | CID | NP-53.9 - Small Value Procurement | April 1,2020 | N/A | April 7,2020 | April 7,2020 | GoP | 59985 | 59985 | 0
| Capacity Building Seminar and Character Education Formation for School Heads and Teachers | CID | NP-53.9 - Small Value Procurement | April 1,2020 | N/A | April 7,2020 | April 7,2020 | GoP | 130000 | 130000 | 0
| Division Writeshop on the Development of Alternative Delivery Materials | CID | NP-53.9 - Small Value Procurement | April 1,2020 | N/A | April 7,2020 | April 7,2020 | GoP | 200000 | 200000 | 0
| Division Training-Workshop on Handling SPED Learners for Transition/Inclusive Education | CID | NP-53.9 - Small Value Procurement | April20,2020 | N/A | April 24,2020 | April 24,2020 | GoP | 84918 | 84918 | 0
| Training -Workshop on Instructional Supervision for Master Teachers | CID | NP-53.9 - Small Value Procurement | April20,2020 | N/A | April 24,2020 | April 24,2020 | GoP | 60360 | 60360 | 0
| Division Training on Content and Pedagogy Grade 7-10 (Music) | CID | NP-53.9 - Small Value Procurement | May 11, 2020 | N/A | May 15, 2020 | May 15, 2020 | GoP | 57150 | 57150 | 0
| Division Training Workshop on Sports Officiating | CID | NP-53.9 - Small Value Procurement | May 11, 2020 | N/A | May 15, 2020 | May 15, 2020 | GoP | 71100 | 71100 | 0
| Division Orientation on LRC/School Library Establishment, Improvement and Management | CID | NP-53.9 - Small Value Procurement | July 13, 2020 | N/A | July 17, 2020 | July 17,2020 | GoP | 45000 | 45000 | 0
| Enhancement-Training Workshop on Delivery of Livelihood and Technology Competency | CID | NP-53.9 - Small Value Procurement | Aug.21,2020 | N/A | Aug.26,2020 | Aug.26,2020 | GoP | 98626 | 98626 | 0
| Conduct of School-Based Management Technical Assistance Meeting/Orientation | YFP | Shopping | 2020-03-01 | N/A | 2020-07-01 | 2020-08-01 | GoP | 10650 | 10650 | 0 | 0
0 | Conduct of Dayaw 2020 | YFP | Shopping | 2020-03-01 | N/A | 2020-07-01 | 2020-08-01 | GoP | 13000 | 13000 | 0 | 0
0 | Roll Out of Grade 11 and 12 Career Guidance Program Module | Research | NP-53.9 - Small Value Procurement | 4/20/2020 | N/A | 04/24/2020 | 04/27/2020 | GoP | 115000 | 115000 | 0 | 0
0 | Research Implementation Review | Research | Shopping | 08/17/2020 | N/A | 08/24/2020 | 8/25/2020 | GoP | 37655 | 37655 | 0 | 0
0 | Training on Qualitative Research | Research | NP-53.9 - Small Value Procurement | 1/27/2020 | N/A | 1/31/2020 | 2020-03-02 | GoP | 93675 | 93675 | 0 | 0
0 | Training on Data Analysis for Math Teachers | Research | NP-53.9 - Small Value Procurement | 4/20/2020 | N/A | 04/24/2020 | 4/27/2020 | GoP | 60675 | 60675 | 0 | 0
0 | Capacity-Building on Applied Research for SDO Personnel | Research | Shopping | 1/27/2020 | N/A | 1/31/2020 | 2020-03-02 | GoP | 23000 | 23000 | 0 | 0
0 | Training on Preparation of Research Instruments for School Heads Questionnaires from Development to Validity, Quality and Reliability Check | Research | NP-53.9 - Small Value Procurement | 4/20/2020 | N/A | 4/24/2020 | 4/27/2020 | GoP | 79925 | 79925 | 0 | 0
0 | Roll -out on School Dental Health Care Program | Dental | Shopping | 1/27/2020 | N/A | 1/31/2020 | 2020-03-02 | GoP | 26200 | 26200 | 0 | 0
0 | Division Orientation on Comprehensive Tobacco Control for School Heads | Medical | Shopping | 2020-03-01 | N/A | 2020-07-01 | 2020-08-01 | GoP | 14000 | 14000 | 0 | 0
0 | Roll-Out on Universal Prevention Curriculum on Substance Abuse: Curriculum 1 and 2 | Medical | NP-53.9 - Small Value Procurement | 4/20/2020 | N/A | 4/24/2020 | 4/27/2020 | GoP | 58880 | 58880 | 0 | 0
0 | Search for Ok sa DepEd Best implementer | Medical | NP-53.9 - Small Value Procurement | 4/20/2020 | N/A | 4/24/2020 | 4/27/2020 | GoP | 56400 | 56400 | 0 | 0
0 | Re-Orientation on Canteen Management | Medical | Shopping | 5/25/2020 | N/A | 5/28/2020 | 5/29/2020 | GoP | 14000 | 14000 | 0 | 0
0 | Training on Mental Health SDO | Medical | Shopping | 2020-03-01 | N/A | 2020-07-01 | 2020-08-01 | GoP | 28000 | 28000 | 0 | 0
0 | Hosting of Regional MANCOM | SDS | NP-53.9 - Small Value Procurement | 2020-03-01 | N/A | 2020-07-01 | 2020-08-01 | GoP | 99890 | 99890 | 0 | 0
0 | Conduct of Division Mancom | SDS | NP-53.9 - Small Value Procurement | 2020-03-01 | N/A | 2020-07-01 | 2020-08-01 | GoP | 109000 | 109000 | 0 | 0
0 | Training for Facilitators' Pool | HRD | NP-53.9 - Small Value Procurement | 2/24/2020 | N/A | 2/27/2020 | 2/28/2020 | GoP | 151820 | 151820 | 0 | 0
0 | Training-Workshop on Professional Ethics, Stress Management, Oral and Written Communication for SDO Personnel | HRD | NP-53.9 - Small Value Procurement | 2/24/2020 | N/A | 2/27/2020 | 2/28/2020 | GoP | 81890 | 81890 | 0 | 0
0 | RPMS-PPST Training | HRD | NP-53.9 - Small Value Procurement | 2/24/2020 | N/A | 2/27/2020 | 2/28/2020 | GoP | 290150 | 290150 | 0 | 0
0 | Gender and Development Training | HRD | NP-53.9 - Small Value Procurement | 4/20/2020 | N/A | 4/24/2020 | 4/27/2020 | GoP | 551000 | 551000 | 0 | 0
0 | Conduct of Teacher and Non-Teaching Induction Program | HRD | NP-53.9 - Small Value Procurement | 5/25/2020 | N/A | 5/28/2020 | 5/29/2020 | GoP | 132422 | 132422 | 0 | 0
0 | Search for Outstanding Teacher and Non-Teaching Personnel | HRD | NP-53.9 - Small Value Procurement | 9/21/2020 | N/A | 9/24/2020 | 9/25/2020 | GoP | 208500 | 208500 | 0 | 0
0 | National Educators' Congress | HRD | NP-53.9 - Small Value Procurement | 4/20/2020 | N/A | 4/24/2020 | 4/27/2020 | GoP | 480000 | 480000 | 0 | 0
0 | Brigada Eskwela Kick Off Program | HRD | NP-53.9 - Small Value Procurement | 4/20/2020 | N/A | 4/24/2020 | 4/27/2020 | GoP | 92500 | 92500 | 0 | 0
0 | Orientation and Election of PTA Federation Officers | SOCMOB | Shopping | 7/20/2020 | N/A | 7/23/2020 | 7/24/2020 | GoP | 14000 | 14000 | 0 | 0
0 | Division Brigada Eskwela Awarding Ceremonies and Partnership Appreciation Program | SOCMOB | NP-53.9 - Small Value Procurement | 9/21/2020 | N/A | 9/24/2020 | 9/25/2020 | GoP | 103000 | 103000 | 0 | 0
0 | Division Roll-Out on DRRM Modules for School Heads (Foundation and Competency Modules) | DRRM | Shopping | 11/23/2020 | N/A | 11/26/2020 | 11/27/2020 | GoP | 35000 | 35000 | 0 | 0
0 | Coordination Planning Workshop on DRRM Pillars for School Facility Coordinators | DRRM | NP-53.9 - Small Value Procurement | 11/23/2020 | N/A | 11/26/2020 | 11/27/2020 | GoP | 60000 | 60000 | 0 | 0
0 | ICT Literacy Training-Workshop for Non-Teaching Personnel | ICT | NP-53.9 - Small Value Procurement | 4/20/2020 | N/A | 4/24/2020 | 4/27/2020 | GoP | 130000 | 130000 | 0 | 0
0 | Division Computer Program Orientation for ICT Coordinators | ICT | NP-53.9 - Small Value Procurement | 6/22/2020 | N/A | 6/25/2020 | 6/26/2020 | GoP | 73500 | 73500 | 0 | 0
0 | Orientation-Workshop on the DepEd Merit Selection Plan | PERSONNEL | NP-53.9 - Small Value Procurement | 4/20/2020 | N/A | 4/24/2020 | 4/27/2020 | GoP | 74000 | 74000 | 0 | 0
0 | Conduct of Training on Asset Management and Inventory of Records | SUPPLY | NP-53.9 - Small Value Procurement | 3/23/2020 | N/A | 3/26/2020 | 3/27/2020 | GoP | 85100 | 85100 | 0 | 0
0 | Orientation-Workshop on the Preparation of FY 2021 Expenditure Matrix and APP CSE and Non CSE | BUDGET | NP-53.9 - Small Value Procurement | 9/21/2020 | N/A | 9/24/2020 | 9/25/2020 | GoP | 153100 | 153100 | 0 | 0
0 | Orientation-Workshop on the Preparation of FY 2022 Budget Proposal | BUDGET | NP-53.9 - Small Value Procurement | 10/26/2020 | N/A | 10/29/2020 | 10/30/2020 | GoP | 81750 | 81750 | 0 | 0
| Prepared by: |  | Appropriate Funds Available: | Funds Available: |  |  | Recomemding Approval: |  |  |  |  | Aprpoved:
| YOLANDA C. PAGULAYAN |  | JOVY CLAIRE V. TUNGCUL | MARIEL A. CAMMAYO |  |  | JESUS B. MAGGAY |  |  |  |  | REYNANTE Z. CALIGUIRAN
| BAC Secretariat-Chairman |  | Administrative Officer V-Budget | Accountant III |  |  | Assistant Schools Division Superintendent |  |  |  |  | Officer In-Charge
[7 empty] | BAC Chairman |  |  |  |  | Office of the Schools Division Superintendent

## how_to_fill_out-definitions
| GUIDE TO PREPARE APP | APP COLUMN HEADER/S
STEP 1 | In the Code (PAP) column, kindly indicate the Procuring Entity's (PEs) internal numbering system or use the Unified Account Codes (UACS) may be used as PAP Codes. Please refer to Joint Circular No.2013-1 COA-DBM-DOF-Unified Accounts Code Structure. | Code (PAP)
STEP 2 | For the Procurement Program/Project column, please align descriptions of program/projects with budget documents and ensure clarity and accuracy in describing each procurement program/project. | Procurement Program/Project
STEP 3 | For PMO/End-User, please indicate the PMO/End-User unit who will implement/utilize the procurement program/project. Multiple end-user units are allowed only if the procurement activity was consolidated by the BAC to procure requirements of the end-user units. | PMO/End-User
STEP 4 | For Mode of Procurement and Schedule for Each Procurement Activity, all modes of procurement are available as a dropdown list and requirements for a specific schedule for Ads/Post of IB/REI, Sub/Open of Bids, Notice of Award, and/or Contract Signing are automatically identified thru the MS Excel formula. Note that for Foreign-funded procurement, please use Others - Foreign-funded procurement as the Mode of Procurement. Kindly indicate a specific period (dates, month, quarter) when each Procurement Activity will be done. Please refer to our website: http://www.gppb.gov.ph/timelines/timelines.htm for the specific periods for each activity. Note: For SVP, IB/REI is similar to RFQ. Ads/Post of IB/REI for Shopping 52.1(b) and NP-SVP (53.9) needs to be posted in PhilGEPS for ABCs above 50k. Notice of Award posting in PhilGEPS is mandatory for all Alternative Modes only for ABCs above 50k. | Mode of Procurement | Schedule for Each Procurement Activity
|  |  | Ads/Post of IB/REI | Sub/Open of Bids | Notice of Award | Contract Signing
STEP 5 | For Source of Funds, a dropdown list is available. If the Source of Funds the PE will use is not included, please indicate "Others" and specify under the Remarks column. | Source of Funds
STEP 6 | For Estimated Budget (PhP), kindly fill out either MOOE or CO columns only. Total ABC column is not editable, but will automatically compute for the total MOOE and CO components of the project. This breakdown is needed for tracking purposes. Finally, please ensure that amounts indicated are aligned with budget documents. | Estimated Budget (PhP)
STEP 7 | Before submission to the GPPB, ensure that the Head of the Procuring Entity (HoPE) approves/signs the APP.
GENERAL INFORMATION
#1 | All Cells with Fill Color Orange needs to be filled out by the Agency. This is a visual reminder of blank or improperly filled out cells.
#2 | To ensure that automated indicator which procurement activity needs to be filled out with specific periods, PE must copy entire Excel row with the mode of procurement for the specific procurement program/project and paste on the last sample row "Negotiated Procurement-53.13" in the template.
#3 | If PE wishes to edit formatting and design of borders, fonts, among others of the APP template, it is suggested to utilize the automated formulas in the template before copying contents and reformatting.
#4 | Per Section of 3.1.1 of DBM Circular No. 2015-7, the Approved Budget for the Contract (ABC) shall be “[t]he amount reflected in the MYOA”. Hence, the ABC in the Annual Procurement Plan (APP) shall be the full amount stated in the MYOA with remarks added on how much will be actually disbursed for that particular fiscal year. Moreover, the Procurement Monitoring Report (PMR) should also reflect full amount in the MYOA if the entire contract was awarded within the fiscal year. Thus, for succeeding years, actual disbursements from the MYOA need not be reflected in the APPs and PMRs, unless current contract with MYOA is terminated and a new procurement activity is undertaken.
DEFINITIONS
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (advertising/posting; submission and receipt/Opening of bids; award of contract; contract signing).
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund
7. Estimated Budget - Agency approved estimate of project/program costs
8. Remarks - brief description of program or project

## data_validation (hidden)
Competitive Bidding | GoP
Limited Source Bidding | Foreign
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement